## BLANK Gantt Chart & Burndown
SCRUM PROJECT MANAGEMENT GANTT CHART
GANTT CHART AND BURNDOWN
[9 empty] | SPRINTS | SPRINT 1
SPRINT 2
SPRINT 3
SPRINT 4
WORK BREAKDOWN STRUCTURE | TASK TITLE | TASK OWNER | AMOUNT OF WORK IN HOURS |  |  | SPRINT | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
|  |  | ESTIMATE | COMPLETED | REMAINING | [5 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Definition and Planning |  | 80 | 81 | -1 | 1 | 2025-03-10 | 2025-03-26 |  | 101.2%
1.1 | Structure and architecture | Entire team | 15 | 13 | 2 | 1 | 2025-03-10 | 2025-03-11 | 2 | 86.67% | bar: WEEK 1 M to WEEK 1 T
1.1.1 | Requirements specification | Entire team | 8 | 8 | 0 | 1 | 2025-03-12 | 2025-03-13 | 2 | 100% | bar: WEEK 1 W to WEEK 1 R
1.2 | User stories | Entire team | 6 | 8 | -2 | 1 | 2025-03-14 | 2025-03-14 | 1 | 133.3% | bar: WEEK 1 F to WEEK 2 F
1.3 | DB architecture and structure | Entire team | 12 | 12 | 0 | 1 | 2025-03-17 | 2025-03-18 | 2 | 100%
1.4 | Microservices definition | Entire team | 5 | 5 | 0 | 1 | 2025-03-19 | 2025-03-19 | 1 | 100%
1.5 | Backend and frontend structure | Entire team | 20 | 20 | 0 | 1 | 2025-03-20 | 2025-03-24 | 5 | 100% | bar: WEEK 2 M to WEEK 3 M
1.6 | Dockerization | Entire team | 14 | 15 | -1 | 1 | 2025-03-25 | 2025-03-26 | 2 | 107.1% | bar: WEEK 3 T to WEEK 3 W
2 | User Service |  | 60 | 85 | -1 | 2 | 2025-04-07 | 2025-04-24 |  | 141.7%
2.1 | Login logout and registration | Carlo S. | 24 | 20 | 4 | 2 | 2025-04-07 | 2025-04-10 | 4 | 83.33% | bar: WEEK 4 M to WEEK 4 R
2.2 | Role management | Riccardo M. | 12 | 13 | -1 | 2 | 2025-04-11 | 2025-04-14 | 4 | 108.3% | bar: WEEK 4 F to WEEK 5 F
2.3 | Profile management | Mattia T. | 24 | 28 | -4 | 2 | 2025-04-15 | 2025-04-18 | 4 | 116.7%
2.4 | User's Books management | Mattia T. | 24 | 24 | 0 | 2 | 2025-04-21 | 2025-04-24 | 4 | 100% | bar: WEEK 5 M to WEEK 6 R
3 | Book Service |  | 77 | 82 | -5 | 3 | 2025-07-07 | 2025-07-23 |  | 106.5%
3.1 | Catalog search and filtering | Mattia T. | 15 | 15 | 0 | 3 | 2025-07-07 | 2025-07-08 | 2 | 100% | bar: WEEK 7 M to WEEK 7 T
3.2 | Catalog staff management | Carlo S. | 20 | 22 | -2 | 3 | 2025-07-07 | 2025-07-09 | 3 | 110% | bar: WEEK 7 M to WEEK 7 W
3.3 | Books details | Carlo S. | 10 | 8 | 2 | 3 | 2025-07-10 | 2025-07-11 | 2 | 80% | bar: WEEK 7 R to WEEK 8 F
3.4 | Books cover management | Mattia T. | 12 | 7 | 5 | 3 | 2025-07-14 | 2025-07-15 | 2 | 58.33%
3.5 | Availabity and copies tracking | Riccardo M. | 20 | 30 | -10 | 3 | 2025-07-18 | 2025-07-23 | 6 | 150% | bar: WEEK 8 M to WEEK 9 W
4 | Reservation Service |  | 89 | 92 | -3 | 4 | 2025-08-04 | 2025-08-21 |  | 103.4%
4.1 | Reservation management | Riccardo M. | 40 | 45 | -5 | 4 | 2025-08-04 | 2025-08-11 | 8 | 112.5% | bar: WEEK 10 M to WEEK 11 F
4.1.1 | Queue management | Mattia T. | 15 | 15 | 0 | 4 | 2025-08-06 | 2025-08-07 | 2 | 100% | bar: WEEK 10 W to WEEK 10 R
4.2 | Analytics | Carlo S. | 12 | 13 | -1 | 4 | 2025-08-11 | 2025-08-12 | 2 | 108.3%
4.3 | User reservations details | Riccardo M. | 6 | 6 | 0 | 4 | 2025-08-12 | 2025-08-12 | 1 | 100%
4.4 | Librarian reservation fulfillment | Riccardo M. | 12 | 10 | 2 | 4 | 2025-08-13 | 2025-08-18 | 6 | 83.33% | bar: WEEK 11 M to WEEK 12 M
4.5 | Librarian reservation completion | Carlo S. | 4 | 3 | 1 | 4 | 2025-08-21 | 2025-08-21 | 1 | 75% | bar: WEEK 12 R
|  |  | ESTIMATE | COMPLETED | REMAINING | DAYS | EST/DAYS | [63 empty] | TOTAL HOURS
| BURNDOWN DATA | TOTAL HOURS | 306 | 340 | -10 | 60 | 5.1 |  |  | DAY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
[6 empty] | ^ Enter number of days |  |  |  | PLAN | 306 | 300.9 | 295.8 | 290.7 | 285.6 | 280.5 | 275.4 | 270.3 | 265.2 | 260.1 | 255 | 249.9 | 244.8 | 239.7 | 234.6 | 229.5 | 224.4 | 219.3 | 214.2 | 209.1 | 204 | 198.9 | 193.8 | 188.7 | 183.6 | 178.5 | 173.4 | 168.3 | 163.2 | 158.1 | 153 | 147.9 | 142.8 | 137.7 | 132.6 | 127.5 | 122.4 | 117.3 | 112.2 | 107.1 | 102 | 96.9 | 91.8 | 86.7 | 81.6 | 76.5 | 71.4 | 66.3 | 61.2 | 56.1 | 51 | 45.9 | 40.8 | 35.7 | 30.6 | 25.5 | 20.4 | 15.3 | 10.2 | 5.1 | 8032
[10 empty] | ESTIMATE | 306 | 299 | 293 | 289 | 285 | 277 | 271 | 265 | 260 | 253 | 246 | 240 | 232 | 225 | 225 | 225 | 218 | 212 | 207 | 205 | 199 | 192 | 185 | 178 | 171 | 164 | 157 | 150 | 145 | 140 | 140 | 126 | 110 | 103 | 98 | 95 | 89 | 88 | 88 | 88 | 80 | 72 | 64 | 58 | 58 | 58 | 50 | 42 | 27 | 13 | 5 | -8 | -21 | -26 | -26 | -26 | -31 | -31 | -31 | -34 | 340
[9 empty] | Enter hours completed per day ----> | HRS COMPLETED | 7 | 6 | 4 | 4 | 8 | 6 | 6 | 5 | 7 | 7 | 6 | 8 | 7 | 0 | 0 | 7 | 6 | 5 | 2 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 5 | 5 | 0 | 14 | 16 | 7 | 5 | 3 | 6 | 1 | 0 | 0 | 8 | 8 | 8 | 6 | 0 | 0 | 8 | 8 | 15 | 14 | 8 | 13 | 13 | 5 | 0 | 0 | 5 | 0 | 0 | 3 | 0 | 7692
[10 empty] | HRS REMAINING | 299 | 293 | 289 | 285 | 277 | 271 | 265 | 260 | 253 | 246 | 240 | 232 | 225 | 225 | 225 | 218 | 212 | 207 | 205 | 199 | 192 | 185 | 178 | 171 | 164 | 157 | 150 | 145 | 140 | 140 | 126 | 110 | 103 | 98 | 95 | 89 | 88 | 88 | 88 | 80 | 72 | 64 | 58 | 58 | 58 | 50 | 42 | 27 | 13 | 5 | -8 | -21 | -26 | -26 | -26 | -31 | -31 | -31 | -34 | -34